## Sheet1
| Date | Duration (hr:min) | Task
Michael Bauer | 2022-01-29 | 0.10417 | Collaboration on Trello board creating user stories. Setting up the project on Github.
Christian Young | 2022-01-29 | 0.083333 | Helped set up user stories and Github stuff. | Name | Total Duration
Kody Kimberl | 2022-01-29 | 0.083333 | Helped with user stories and Github setup | Michael Bauer | 1900-01-02 15:05
Kody Kimberl | 2022-01-29 | 0.010417 | Formatted worklog | Christian Young | 1900-01-01 03:05
Andrew Palmer | 2022-01-29 | 0.020833 | Helped set up github | Kody Kimberl | 1900-01-02 11:30
Andrew Palmer | 2022-01-29 | 0.020833 | Helped with user stories | Andrew Palmer | 1899-12-31 21:50
Kody Kimberl | 2022-01-29 | 0.010417 | Added UC1 and UC2 descriptions | Total: | 1900-01-10 03:30
Michael Bauer | 2022-01-31 | 0.020833 | Filling out user stories from the Trello board
Michael Bauer | 2022-02-02 | 0.03125 | Further progress of the Trello board user stories
Kody Kimberl | 2022-02-03 | 0.052083 | Added UC9-14&16-17 descriptions
Kody Kimberl | 2022-02-03 | 0.0034722 | Added initial priorities for use cases and sorted based on these
Kody Kimberl | 2022-02-03 | 0.0069444 | Set up planning poker
Michael Bauer | 2022-02-03 | 0.083333 | Planning Poker, discussion on implementation and design of some site pages and database
Kody Kimberl | 2022-02-03 | 0.083333 | Planning Poker, discussion on implementation and design of some site pages and database
Christian Young | 2022-02-03 | 0.083333 | Planning Poker, discussion on implementation and design of some site pages and database
Andrew Palmer | 2022-02-03 | 0.083333 | Planning Poker, discussion on implementation and design of some site pages and database
Kody Kimberl | 2022-02-04 | 0.1875 | Filling out Project Plan and Group Contract Documents
Andrew Palmer | 2022-02-04 | 0.125 | Filling out Project Plan and Group Contract Documents
Christian Young | 2022-02-04 | 0.0625 | Filling out Project Plan and Group Contract Documents
Michael Bauer | 2022-02-08 | 0.083333 | Filled out slides for Presentation 1. Stubbed out navigation on the application and pushed to GitHub for merger.
Christian Young | 2022-02-09 | 0.020833 | Added to and cleaned up presentation slides
Andrew Palmer | 2022-02-09 | 0.020833 | Added to and cleaned up presentation slides
Kody Kimberl | 2022-02-09 | 0.020833 | Additional work on presentation
Andrew Palmer | 2022-02-09 | 0.041667 | Setting up firebase with Angular
Michael Bauer | 2022-02-12 | 0.125 | Set up Firebase and Firestore, created a joint Gmail to be used for Firestore
Christian Young | 2022-02-12 | 0.097222 | Worked on Firebase and Database Models
Kody Kimberl | 2022-02-12 | 0.097222 | Worked on Firebase and Database Models
Andrew Palmer | 2022-02-12 | 0.097222 | Worked on Firebase and Database Models
Michael Bauer | 2022-02-12 | 0.097222 | Worked on Firebase and Database Models
Michael Bauer | 2022-02-15 | 0.29167 | Established connections to Firebase. Created services for the Questions model. Created the layout for the navigation bar and the home page.
Kody Kimberl | 2022-02-17 | 0.041667 | Worked on flagging functionality
Michael Bauer | 2022-02-17 | 0.052083 | Pre-meeting
Kody Kimberl | 2022-02-17 | 0.052083 | Pre-meeting
Christian Young | 2022-02-17 | 0.03125 | Pre-meeting
Andrew Palmer | 2022-02-17 | 0.020833 | Pre-meeting
Kody Kimberl | 2022-02-18 | 0.03125 | Finishing question flagging
Andrew Palmer | 2022-02-18 | 0.03125 | Finishing question flagging
Christian Young | 2022-02-18 | 0.041667 | Set up question creation service + some html for question asking page
Christian Young | 2022-02-19 | 0.03125 | Spent some time fixing up package.json for local errors + basic form html done, question adding functionality still needed + NullInjectionError on ask page load?
Andrew Palmer | 2022-02-19 | 0.1875 | User Auth
Kody Kimberl | 2022-02-19 | 0.1875 | User Auth
Christian Young | 2022-02-19 | 0.041667 | Fixed errors on form, is now submittable
Michael Bauer | 2022-02-23 | 0.125 | Added and adjusted functionality to the navbar, home page, and other flow of the app
Kody Kimberl | 2022-02-24 | 0.11458 | CSS and Technical Doc
Andrew Palmer | 2022-02-24 | 0.11458 | CSS and Technical Doc
Christian Young | 2022-02-24 | 0.20833 | Helped decide some formatting on app, finished Technical Document, question adding implementation almost done
Michael Bauer | 2022-02-24 | 0.25 | Helped with technical document and formatting of the app. Coded with Christian to get the question adding implementation.
Andrew Palmer | 2022-02-26 | 0.10417 | Sprint 2 Planning, Sprint 1 Review, and Finishing Question Asking
Kody Kimberl | 2022-02-26 | 0.10417 | Sprint 2 Planning, Sprint 1 Review, and Finishing Question Asking
Christian Young | 2022-02-26 | 0.11458 | Sprint 2 Planning, Sprint 1 Review, and Finishing Question Asking
Michael Bauer | 2022-02-26 | 0.11458 | Sprint 2 Planning, Sprint 1 Review, and Finishing Question Asking
Michael Bauer | 2022-03-03 | 0.125 | Making Question View show individual questions, filtering by answered, and formatting questions
Kody Kimberl | 2022-03-03 | 0.03125 | Making Question View show individual questions
Andrew Palmer | 2022-03-03 | 0.020833 | Updating formatting for home page
Christian Young | 2022-03-03 | 0.020833 | Updating formatting for home page
Kody Kimberl | 2022-03-03 | 0.020833 | Updating formatting for home page
Michael Bauer | 2022-03-03 | 0.020833 | Updating formatting for home page
Michael Bauer | 2022-03-03 | 0.1875 | Coding question view
Kody Kimberl | 2022-03-04 | 0.125 | Fixing collapse issues
Michael Bauer | 2022-03-04 | 0.10417 | CSS styling throughout application
Michael Bauer | 2022-03-08 | 0.16667 | CSS styling and further implementation of question view
Kody Kimberl | 2022-03-08 | 0.020833 | Helping with comment component
Christian Young | 2022-03-08 | 0.041667 | Created service that adds an answer to the answers collection on the database
Kody Kimberl | 2022-03-08 | 0.020833 | Work on Presentation 2
Michael Bauer | 2022-03-09 | 0.20833 | Work on comments/answers
Kody Kimberl | 2022-03-09 | 0.020833 | Helping with add comment
Kody Kimberl | 2022-03-10 | 0.013889 | Helping with add answer
Christian Young | 2022-03-10 | 0.083333 | Implemented redirection to the new question's page after submitting it
Kody Kimberl | 2022-03-12 | 0.29167 | Getting testing setup, passing, GitHub CI, and mocking database and other components
Andrew Palmer | 2022-03-15 | 0.041667 | Starting Security Evaluation for Sprint 2.
Andrew Palmer | 2022-03-24 | 0.0625 | Finished Security Evaluation for Sprint 2.
Michael Bauer | 2022-03-21 | 0.0625 | Trello board set up for Sprint 3
Andrew Palmer | 2022-03-21 | 0.0625 | Trello board set up for Sprint 3
Kody Kimberl | 2022-03-21 | 0.0625 | Trello board set up for Sprint 3
Christian Young | 2022-03-21 | 0.0625 | Trello board set up for Sprint 3
Christian Young | 2022-03-25 | 0.041667 | Spent some time reading through the TypeScript style guide, and cleaned up some of the code
Kody Kimberl | 2022-03-30 | 0.20833 | Getting showing names on answers and comments set up
Michael Bauer | 2022-03-31 | 0.1875 | Finished all functionality of Question View page. corrected styling on page as well.
Kody Kimberl | 2022-03-31 | 0.083333 | Adding Comments to Answers
Christian Young | 2022-04-01 | 0.083333 | Cleaned up code
Christian Young | 2022-04-07 | 0.083333 | Admin page shows flagged questions, their reasoning for flagging, and a button for removal. Also helped code
Michael Bauer | 2022-04-07 | 0.125 | Group meeting/group coding for search functionality. Inital coding for the profile page.
Kody Kimberl | 2022-04-07 | 0.11458 | Group meeting/group coding. Set up search functionality and accessing word list
Andrew Palmer | 2022-04-07 | 0.10417 | Begun adding question search functionality
Christian Young | 2022-04-08 | 0.15625 | Added ability for admins to remove flagged questions; clears the question document from its collection, removes answers, and removes the id from the user's list of asked questions
Michael Bauer | 2022-04-08 | 0.083333 | Further progression on the Profile page. not fully complete.
Kody Kimberl | 2022-04-08 | 0.03125 | Helping resolve profile question displaying issue
Michael Bauer | 2022-04-08 | 0.041667 | Working on profile questions
Andrew Palmer | 2022-04-09 | 0.0625 | Completing search functionality
Kody Kimberl | 2022-04-09 | 0.0625 | Completing search functionality
Kody Kimberl | 2022-04-09 | 0.0069444 | Reviewing Profile PR
Kody Kimberl | 2022-04-16 | 0.03125 | Troubleshooting test errors
Kody Kimberl | 2022-04-16 | 0.0069444 | Fixing profile circle
Kody Kimberl | 2022-04-16 | 0.03125 | Fixing initial question loading on home and footer css
Kody Kimberl | 2022-04-16 | 0.041667 | Adjusting mobile formatting
Christian Young | 2022-04-19 | 0.041667 | Functionality in place for upvoting and downvoting; doesn't work yet though
Kody Kimberl | 2022-04-21 | 0.041667 | Meeting to discuss final Sprint and troubleshoot
Kody Kimberl | 2022-04-21 | 0.010417 | Fixing issues discussed at end of meeting
Michael Bauer | 2022-04-21 | 0.11458 | Upvoting and Downvoting implemented + admin page link, Meeting to discuss final sprint
Christian Young | 2022-04-21 | 0.072917 | Upvoting and Downvoting implemented + admin page link
Kody Kimberl | 2022-04-23 | 0.09375 | Various fixes and updates for deleting/admin
Michael Bauer | 2022-04-23 | 0.15625 | Assisting with functionality for deleting/admin, functionality to delete comments from questions and answers
Kody Kimberl | 2022-04-23 | 0.41667 | Completing tests for all services
Christian Young | 2022-04-24 | 0.041667 | Moved question voting to answers; messed with css to make it look a little better
Andrew Palmer | 2022-04-24 | 0.083333 | Filled out accessibility assessment and sprint 3 evaluation
Andrew Palmer | 2022-04-27 | 0.1875 | Working on Final report and other documentation
Michael Bauer | 2022-04-27 | 0.1875 | Working on Final report and other documentation
Christian Young | 2022-04-27 | 0.1875 | Working on Final report and other documentation
Kody Kimberl | 2022-04-27 | 0.0625 | Working on Final report
Andrew Palmer | 2022-04-28 | 0.25 | Working on Final report, user manual, and codebase cleanup
Kody Kimberl | 2022-04-28 | 0.083333 | Assisting with final changes
Kody Kimberl | 2022-04-28 | 0.125 | Continued assisting with final changes
Christian Young | 2022-04-28 | 0.27083 | Assisted with final touch-ups and cleaned up code
Michael Bauer | 2022-04-28 | 0.27083 | Assisted with final touch-ups and cleaned up code
Kody Kimberl | 2022-04-29 | 0.33333 | Fixing git issues, group work finishing up the project
Michael Bauer | 2022-04-29 | 5:00 | group work finishing up the project
Christian Young | 2022-04-29 | 0.125 | group work finishing up the project
Andrew Palmer | 2022-04-29 | 0.16667 | Finalizing project for final submission